## Q1 network
|  |  | 4 | 2 | 12 |  |  |  | 14 | 7 | 18
|  |  | 2 |  | 2 |  |  |  | 0 |  | 0
|  |  | 6 | 8 | 14 |  |  |  | 14 | 4 | 18
0 | 1 | 4 | 4 | 3 | 10 | 10 | 5 | 14 |  |  |  | 18 | 8 | 22
0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  |  | 0 |  | 0
0 | 4 | 4 | 4 | 6 | 10 | 10 | 4 | 14 |  |  |  | 18 | 4 | 22
|  |  | 4 | 4 | 8 | 8 | 6 | 16
|  |  | 2 |  | 2 | 2 |  | 2
|  |  | 6 | 4 | 10 | 10 | 8 | 18
[9 empty] | ES | ID | EF
[9 empty] | LS | DUR | LF

## Q1 PV plan
Schedule Information | [5 empty] | Baseline PV ($00)
Activity / Work Package | Duration | Earliest Start | Latest Finish | Slack | Total Planned Value ($00) | Planned Value up to the end of the Time period below
[6 empty] | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22
1 | 4 | 0 | 4 | 0 | 8 | Planned Value up to the end of the Time period below 2: 4; Planned Value up to the end of the Time period below 4: 4
2 | 8 | 4 | 14 | 2 | 40 | Planned Value up to the end of the Time period below 6: 10; Planned Value up to the end of the Time period below 8: 10; Planned Value up to the end of the Time period below 10: 10; Planned Value up to the end of the Time period below 12: 10
3 | 6 | 4 | 10 | 0 | 30 | Planned Value up to the end of the Time period below 6: 10; Planned Value up to the end of the Time period below 8: 15; Planned Value up to the end of the Time period below 10: 5
4 | 4 | 4 | 10 | 2 | 20 | Planned Value up to the end of the Time period below 6: 10; Planned Value up to the end of the Time period below 8: 10
5 | 4 | 10 | 14 | 0 | 40 | Planned Value up to the end of the Time period below 12: 20; Planned Value up to the end of the Time period below 14: 20
6 | 8 | 8 | 18 | 2 | 60 | Planned Value up to the end of the Time period below 10: 20; Planned Value up to the end of the Time period below 12: 20; Planned Value up to the end of the Time period below 14: 10; Planned Value up to the end of the Time period below 16: 10
7 | 4 | 14 | 18 | 0 | 20 | Planned Value up to the end of the Time period below 16: 10; Planned Value up to the end of the Time period below 18: 10
8 | 4 | 18 | 22 | 0 | 30 | Planned Value up to the end of the Time period below 20: 20; Planned Value up to the end of the Time period below 22: 10
Total PV by period | [5 empty] | 4 | 4 | 30 | 35 | 35 | 50 | 30 | 20 | 10 | 20 | 10
Cummulative PV by period | [5 empty] | 4 | 8 | 38 | 73 | 108 | 158 | 188 | 208 | 218 | 238 | 248

## Q1 status report
Status Report: Ending Period 2
Task | % Complete | EV | AC | PV | CV | SV | CPI | SPI
1 | 50 | 4 | 4 | 4 | 0 | 0 | 1 | 1
Cumulative totals |  | 4 | 4 | 4 | 0 | 0 | 1 | 1
Status Report: Ending Period 4
Task | % Complete | EV | AC | PV | CV | SV | CPI | SPI
1 | 100 | 8 | 10 | 8 | -2 | 0 | 0.8 | 1
Cumulative totals |  | 8 | 10 | 8 | -2 | 0 | 0.8 | 1
Status Report: Ending Period 6
Task | % Complete | EV | AC | PV | CV | SV | CPI | SPI
1 | 100 | 8 | 10 | 8 | -2 | 0 | 0.8 | 1
2 | 25 | 2.5 | 15 | 10 | -12.5 | -7.5 | 0.16667 | 0.25
3 | 33 | 3.33 | 12 | 10 | -8.67 | -6.67 | 0.2775 | 0.333
4 | 0 | 0 | 0 | 10 | 0 | -10 | 0 | 0
Cumulative totals |  | 13.83 | 37 | 38 | -23.17 | -24.17 | 0.37378 | 0.36395
Status Report: Ending Period 8
Task | % Complete | EV | AC | PV | CV | SV | CPI | SPI
1 | 100 | 8 | 10 | 8 | -2 | 0 | 0.8 | 1
2 | 30 | 6 | 20 | 20 | -14 | -14 | 0.3 | 0.3
3 | 60 | 15 | 25 | 25 | -10 | -10 | 0.6 | 0.6
4 | 0 | 0 | 0 | 20 | 0 | -20 | 0 | 0
Cumulative totals |  | 29 | 55 | 73 | -26 | -44 | 0.52727 | 0.39726
Status Report: Ending Period 10
Task | % Complete | EV | AC | PV | CV | SV | CPI | SPI
1 | 100 | 8 | 10 | 8 | -2 | 0 | 0.8 | 1
2 | 60 | 18 | 30 | 30 | -12 | -12 | 0.6 | 0.6
3 | 100 | 30 | 40 | 30 | -10 | 0 | 0.75 | 1
4 | 50 | 10 | 20 | 20 | -10 | -10 | 0.5 | 0.5
5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 30 | 6 | 24 | 20 | -18 | -14 | 0.25 | 0.3
Cumulative totals |  | 72 | 124 | 108 | -52 | -36 | 0.58065 | 0.66667
Status Report: Ending Period 12
Task | % Complete | EV | AC | PV | CV | SV | CPI | SPI
1 | 100 | 8 | 10 | 8 | -2 | 0 | 0.8 | 1
2 | 100 | 40 | 50 | 40 | -10 | 0 | 0.8 | 1
3 | 100 | 30 | 40 | 30 | -10 | 0 | 0.75 | 1
4 | 100 | 20 | 40 | 20 | -20 | 0 | 0.5 | 1
5 | 50 | 10 | 30 | 20 | -20 | -10 | 0.33333 | 0.5
6 | 50 | 20 | 40 | 40 | -20 | -20 | 0.5 | 0.5
Cumulative totals |  | 128 | 210 | 158 | -82 | -30 | 0.60952 | 0.81013

## Q1 indices table
Period | SPI | CPI | PCIB
2 | 1 | 1 | 0.025316 | SPI = EV/PV
4 | 1 | 0.8 | 0.050633 | CPI = EV/AC
6 | 0.364 | 0.374 | 0.087532 | PCIB = EV/BAC
8 | 0.397 | 0.527 | 0.18354
10 | 0.667 | 0.581 | 0.4557
12 | 0.81 | 0.61 | 0.81013

## Q1 summary graph
Period | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22
($00) PV | 4 | 8 | 38 | 73 | 108 | 158 | 188 | 208 | 218 | 238 | 248
AC | 4 | 10 | 37 | 55 | 124 | 210
EV | 4 | 8 | 13.83 | 29 | 72 | 128
SPI | 1 | 1 | 0.364 | 0.397 | 0.667 | 0.81
CPI | 1 | 0.8 | 0.374 | 0.527 | 0.581 | 0.61
PCIB | 0.03 | 0.05 | 0.09 | 0.184 | 0.456 | 0.81
Based on the data provided, and the calculations for CPI and SPI that can be derived from it,
this project is running late and is over budget. Cost Performance Index (CPI) which is the ratio
of the value earned at period 12 and the costs incurred to this point, is below 1 which indicates
that at this period of time, the project's earned value is less than its actual costs meaning that
the project is running over budget. Schedule Performance Index (SPI) which is the ratio of the
value earned at period 12 and the value planned to this point, is below 1 indicating that at this
period of time, the project’s earned value is less than its predicted value meaning that the
project is running behind schedule (late).

## Q2 Network Diagram
Activity | Preceding activity | Best A | Likely M | Worst B | Time est (days) | St.Dev | Variance | ES | EF | DUR | LS | LF | ES | ID | EF | slack
a. Rough in walls | - | 11 | 12 | 13 | 12 | 0.33333 | 0.11111 | 0 | 12 | 12 | 0 | 12 |  |  |  | 0
b. Build the bar | a | 4 | 6 | 11 | 6.5 | 1.1667 | 1.3611 | 12 | 19 | 6.5 | 14 | 21 | LS | DUR | LF | 2
c. run HVAC | - | 12 | 15 | 30 | 17 | 3 | 9 | 0 | 17 | 17 | 4 | 21 |  |  |  | 4
d. rough in electrical | b,c | 12 | 15 | 20 | 15.3333 | 1.3333 | 1.7778 | 19 | 34 | 15.3333 | 21 | 36 |  |  |  | 2
e. complete flooring | a | 7 | 12 | 22 | 12.8333 | 2.5 | 6.25 | 12 | 25 | 12.8333 | 12 | 25 |  |  |  | 0
f. get licenses | e | 2 | 17 | 19 | 14.8333 | 2.8333 | 8.0278 | 25 | 40 | 14.8333 | 25 | 40 |  |  |  | 0
g. install fire alarm | c,d,e | 13 | 17 | 19 | 16.6667 | 1 | 1 | 34 | 51 | 16.6667 | 36 | 53 |  |  |  | 2
h. deliver kitchen equip | e,f | 9 | 14 | 19 | 14 | 1.6667 | 2.7778 | 40 | 54 | 14 | 40 | 54 |  |  |  | 0
i. exposed ceiling reviews | c,g | 11 | 13 | 20 | 13.8333 | 1.5 | 2.25 | 51 | 65 | 13.8333 | 53 | 67 |  |  |  | 2
j. build stage | g,h | 12 | 13 | 16 | 13.3333 | 0.66667 | 0.44444 | 54 | 67 | 13.3333 | 54 | 67 |  |  |  | 0
k. sound system | j,i | 9 | 13 | 23 | 14 | 2.3333 | 5.4444 | 67 | 81 | 14 | 67 | 81 |  |  |  | 0
Z-Score | [7 empty] | slack: 51 | i | 65
0.32256 | [7 empty] | slack: 2 | Exposed ceiling reviews | 2
[8 empty] | LF: 34; ES: g; ID: 51; slack: 53 | 14 | 67
[12 empty] | 2 | Install fire alarm | 2
[12 empty] | 36 | 17 | 53
| 0 | c | 17
| 4 | run HVAC | 4
| 4 | 17 | 21 |  |  |  |  | ES: 19; EF: d; DUR: 34 | [5 empty] | 67 | k | 81
[8 empty] | ES: 2; EF: Rough in Electrical; DUR: 2 | [5 empty] | 0 | Sound system | 0
[8 empty] | ES: 21; EF: 15; DUR: 36 | [5 empty] | 67 | 14 | 81
[19 empty] | 54 | j | 67
[19 empty] | 0 | Build stage | 0
[19 empty] | 54 | 13 | 67
[5 empty] | 12 | b | 19
[5 empty] | 2 | Build the bar | 2
[5 empty] | 14 | 7 | 21
| 0 | a | 12 |  | 12 | e | 25 | LF: 40; ES: h; ID: 54
| 0 | Rough in walls | 0 |  | 0 | Flooring | 0 | LF: 0; ES: Deliver kitchen equip; ID: 0
| 0 | 12 | 12 |  | 12 | 13 | 25 | LF: 40; ES: 14; ID: 54
[8 empty] | 25 | f | 40
[8 empty] | 0 | Get licenses | 0
Answers | [7 empty] | ES: 25; EF: 15; DUR: 40
A. All redundant links are shown with a red 'X' through then. They are left in to show the initial path.
B. Critical path identified with red arrows.
C. Slack is calculated in the network diagram
D. The most sensitive elements in the network diagram are activity b, d, g, I which all the smallest non zero amount of slack (2) and the least sensitive
element in the network diagram is c which has the largest non zero amount of slack (4)
E. The predicted project duriation for the critical path is TE = 81
F. The Z score for this project given TE and TS is 0.323 which when converted to the probability of arounf 0.626 or 62.6% chance of finishing
thr project on time assuming TE is the predicted project duration.